## Sheet1
Date | Notes | Meeting | Meeting notes | Key Milestones
29/09/2020 to 5/10/2020 | Began constructing my project propsal | No
6/10/2020 to 12/10/2020 | I had to correct many parts of my proposing many unnessary aspect | Yes | This meeting helped establish the direction of my proposal and discussed key issues I may encounter
13/10/2020 to 19/10/2020 | I began to prepare for my literature review and finding suitable | Yes | The propsal was discussed and there was still major issues with the scope that I was proposing | Project proposal handed in
source relevant to the project
20/10/2020 to 26/10/2020 | Key issues/themes and areas of knowledge complete | No
27/10/2020 to 31/10/2020 | I had to redo parts of my review as it didn’t accomplish the purpose | Yes | The general direction of my project was discussed and a focus on what I am measuring and what | Literature review handed in
| of the literature review |  | parameters I will use. Furthermore, we discussed starting the design and programming of the simulation
31/10/2020 to 13/11/2020 | Absence due to Extenuating Circumstances
14/11/2020 to 20/11/2020 | Began to design my program and completed my first UML class diagram draft | Yes | Further discussion on the scope of my investigation and understanding the amount of simulations needed | Created a Trello account
In addition, discussed key errrors in my project such as attempting to measure complexity of the methods
21/11/2020 to 27/11/2020 | Description of aims and objectives complete and began working on my program | No |  | Completed a functioning Deck and dealer class
28/11/2020 to 4/12/2020 | Research and design of my simulation plan to handle the data | Yes | Discussion on how my program is going, the performance parameters and how it is going to work | UML class diagram complete
and Issues addressed in the project complete
5/12/2020 to 11/12/2020 | Re-design of my simulation model to cater to the amount of simulations | No |  | Complete my first simulation using the Generic Strategy
conducted and parameter list
12/12/2020 to 18/12/2020 | Finalised my project progress report and completed my first simulation | No |  | Handed in Progress report
a card counting method
Semester 2
Week 1 | No change (exam and coursework due) | No
Week 2 | Refined the completed Hi-Lo method | Yes | Project still has a scope problem and needs to be clearer on how I am addressing the varibale betting across
|  | Yes | Furthermore, it was discussed the need to complete the application to gather the data as soon as possible
Week 3 | KO-count completed and run successfully across some parameters | No
Week 4 | All parameters completed as well as the remaining methods able to run simulations | No |  | All methods able to run across all the parameters
Week 5 | Testing my application utilizing unit testing- Fixed bug that let players bet with <0 chips | No
Week 6 | Data collection | No |  | The start of data collection which provides the essential raw data
Week7 | Further Data collection | No
Week 8-9 | Noticed a really big bug that caused inaccuracies in the majority of the data collected | No |  | Recollected all my results and performed analysis and evaluation on it
True count wasn't accurate as deck size did not change with the input of simulations
but worked fine for test case which led to it being undetected to this point